## Risk Register
Project: AHI Real-Time Marketing Data Application Project
Date: April 20XX – November 20XX
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Complex analytical and e-commerce requirements exceeding initial development estimates or unforeseen integration costs | Project exceeds the approved $250,000 fixed budget | Reduced Year 1 ROI below the 20% target; potential financial shortfall and executive sponsor scrutiny | Oscar Money / Cary Manning | Financial | 3 | 4 | 12 | Monthly burn-rate analysis shows cost variance (CV) > 5% or vendor invoices exceeding milestone caps | Mitigate: Implement strict EVM and milestone-based vendor payments. Contingency: De-scope Version 2 secondary features to protect core budget.
2 | Inadequate initial requirement definition or insufficient stakeholder and focus-group feedback during UI/UX prototyping | Application design flaws and usability defects identified late | Delays in app launch, negative user adoption, and increased rework expenses | Cal Hamer (Product Owner) | Technical / Scope | 3 | 4 | 12 | Negative feedback during sprint reviews or high rejection rate (>10%) during initial design reviews | Mitigate: Conduct iterative design reviews with Marketing SMEs. Contingency: Utilize the 3-day Design phase buffer for rapid UI/UX patching.
3 | Underestimating the complexity of real-time data streaming, sentiment analysis, and multi-system integration | Development schedule slippage and missed sprint deadlines | Delays the planned October go-live, missing peak skincare industry market opportunities | Cary Manning (Project Manager) | Schedule | 4 | 4 | 16 | Sprint burndown charts falling > 15% behind planned velocity for two consecutive sprints | Mitigate: Run 2-week Agile sprints with MVP prioritization and schedule buffers. Contingency: Reallocate senior dev resources to critical path tasks.
4 | Existing server hardware, network bandwidth, and database storage unable to handle real-time data streaming loads | IT infrastructure performance bottlenecks and system crashes | Reduced ROI, app launch delays, poor customer experience, and transaction failures | Priya Service (IT Lead) | Technical / IT | 2 | 4 | 8 | Server CPU utilization > 80% or query latency exceeding 3 seconds during integration testing | Mitigate: Execute $30k HW/SW and storage upgrades during Dev/Test phases. Contingency: Provision scalable cloud overflow capacity.
5 | Internal IT and marketing teams lack specialized mobile app development and real-time analytics engineering skills | Insufficient internal development capacity to build the app in-house | Severe development bottlenecks, quality compromises, and launch delays | Cary Manning / Cal Hamer | Resource / HR | 4 | 3 | 12 | Resource allocation conflicts or lack of qualified developers assigned during Design phase | Mitigate: Contract an experienced external development vendor ($180k budget). Contingency: Onboard external contractor specialists immediately.
6 | External e-commerce transaction vulnerabilities or insecure customer data storage | Data breach, unauthorized access, or non-compliance with payment security standards | Legal liability, financial penalties, brand reputation damage, and customer loss | Priya Service (IT Lead) | Security | 2 | 5 | 10 | Security audit failure or critical vulnerabilities flagged during Test phase penetration testing | Mitigate: Invest $20k in app security upgrades and encryption. Contingency: Deploy immediate security patches and isolate affected services.
7 | Third-party data vendors fail to deliver reliable, real-time market and competitive sales data feeds | Data feed outages, high latency, or corrupted industry metrics | Inaccurate market share analytics and delayed marketing strategic decisions | Priya Service / Ram Samuels | Operational | 3 | 3 | 9 | Data feed downtime > 1 hour or automated schema mismatch alerts triggered | Mitigate: Establish strict vendor SLAs under the $5k data feed contract. Contingency: Implement local caching to display latest validated data.
8 | Marketing personnel and internal stakeholders receive insufficient training on new analytics tools | Low user adoption and improper utilization of the real-time app | Delayed realization of business benefits and reduced operational efficiency | Ram Samuels (Marketing Director) | Operational / Training | 3 | 3 | 9 | User training attendance < 80% or low daily active users post-launch | Mitigate: Conduct mandatory hands-on training workshops in October. Contingency: Deploy the 2 new IT technicians for dedicated desk-side support.
Total Risk Score | [7 empty] | 88 | Risk Exposure: Moderate to High
| Probability risk rating |  |  | Impact risk rating
| 5: High | 80% - 100% |  | 5: High | Major project failure / > $50k variance
| 4: High to moderate | 60% - 79% |  | 4: High to moderate | Significant schedule delay / budget impact
| 3: Moderate | 40% - 59% |  | 3: Moderate | Moderate delay / manageable cost impact
| 2: Moderate to low | 20% - 39% |  | 2: Moderate to low | Minor inconvenience / low rework
| 1: Low | < 20% |  | 1: Low | Negligible operational impact