## Quality Mgt Plan Template
Quality management plan for project:
Part I: Project objectives (reference project charter)
1 Build a centralized app to provide real-time marketing data and replace disconnected spreadsheets
2 Give customers a clean mobile interface to browse products, check prices, and place secure orders
3 Track skincare industry trends, customer opinions, and competitor market share in real time
4 Complete UI/UX design and scope IT infrastructure upgrades (May 20XX / 30 days)
5 Build the working prototype and set up backend IT interfaces (Jun–Aug 20XX / 90 days)
6 Run beta testing and security checks with marketing users and focus groups (Sep 20XX / 30 days)
7 Launch the app, train marketing staff, and collect user feedback for Version 2 (Oct–Nov 20XX / 60 days)
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Cary Manning | Project Manager | X | X
Cal Hamer | QA Lead (Product Owner) | X | X | X | X
Priya Service | QC Lead (IT Lead) | X | X | X | X
Ram Samuels | SME (Marketing Director) |  |  | X
Keiko Tanaka | Marketing Core Team | X |  | X
Jose Garcia | Marketing Core Team | X |  | X
Mary Smithers | Project Sponsor |  | X | X | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inspections)
Audit design and vendor selection process |  |  | Verify final app design specifications
Audit prototype development and sprint progress |  |  | Verify working app prototype and IT interfaces
Audit beta test protocol and security reviews |  |  | Verify beta test results and security scan sign-off
Audit launch readiness and staff training plan |  |  | Verify final launch checklist and staff training completion
Audit user feedback collection process |  |  | Verify performance metrics and Version 2 upgrade roadmap