## Comm Mgt Plan Template
Communications plan
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Project Kick-off | Cary Manning (PM) | Mary Smithers (Sponsor), Mary Lin (CEO), Ram Samuels, Priya Service, Oscar Money, Cal Hamer, Core Team | April 20XX (Project Start) | In-person meeting / Video call & deck | Align leadership on project goals, confirm team roles, review the hybrid delivery approach, and lock in the $250k budget and timeline.
Daily Standup | Cal Hamer (Product Owner) / Dev Lead | Dev Team, Priya Service (IT Lead), Keiko Tanaka, Jose Garcia | Daily (15 mins) (Jun–Aug Dev Phase) | Virtual standup / Jira board & Slack | Catch daily roadblocks early, track sprint burndown velocity, and keep app feature builds on schedule.
Weekly PM Status Update | Cary Manning (PM) | Core Project Team, Ram Samuels (Marketing), Priya Service (IT) | Weekly | 1-page PDF summary & brief status call | Review milestone progress, track spending against our $250k cap, and manage active risks.
Monthly Leadership Briefing | Cary Manning (PM) / Mary Smithers (Sponsor) | Mary Lin (CEO), Oscar Money (Finance) | Monthly | Executive slide deck & brief meeting | Update the executive team on milestone health, budget burn, and tracking toward our 20% Year 1 ROI target.
Sprint Review & Demo | Cal Hamer (Product Owner) | Mary Smithers (Sponsor), Ram Samuels (Marketing), Focus Group Leads, Core Team | Every 2 weeks (Sprint end) | Live working software demo & feedback form | Showcase completed features, gather immediate user feedback, and validate dashboard analytics and checkout flows.
Phase Gate Reviews | Cary Manning (PM) | Mary Smithers (Sponsor), Oscar Money (Finance), Priya Service (IT) | End of each phase (May, Aug, Sep, Oct) | Review meeting & formal sign-off sheet | Verify all phase exit deliverables and get sponsor approval before releasing funds for the next phase.
Customer Beta & Focus Groups | Ram Samuels (Marketing) / Keiko Tanaka, Jose Garcia | External Customer Focus Groups, Marketing Research Team | September 20XX (Test Phase) | Hands-on test sessions & in-app feedback | Test real-world usability of product catalogs, checkout flows, and real-time market data dashboards.
Staff Application Training | Ram Samuels (Marketing) / 2 IT Technicians | AHI Marketing and Sales staff | October 20XX (Pre-launch) | Hands-on workshop & user quick-guides | Ensure the marketing team knows how to pull reports, read sentiment trends, and manage daily workflows before go-live.
Project Closeout & Handover | Cary Manning (PM) | Mary Lin (CEO), Mary Smithers (Sponsor), All Project Stakeholders | November 20XX (Project End) | Final report document & presentation | Close out contracts, review final spend against the $250k budget, evaluate ROI, and hand over the Version 2 roadmap.