## Sprint Backlog
Sprint Backlog for Project: AHI Real-Time Marketing Data App
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0001 Customer Needs 1 | Lead: Cal | User Story: Easier Access to AHI Products and Pricing | 75
| Dev Lead | Task 1: Develop visible product catalog for skincare devices | 20
| Keiko | Task 2: List easy to view pricing for all device options | 15
| Dev Lead | Task 3: Build device detail screen with product specifications | 18
| Jose | Task 4: Implement product search and category filtering | 12
| Dev Lead | Task 5: Enable customer account login and profile access | 10
0002 Customer Needs 2 | Lead: Priya | User Story: Secure Invoicing and Order Processing | 75
| Priya | Task 1: Develop secure payment transaction feature | 25
| Dev Lead | Task 2: Program automated invoice generation function | 15
| Jose | Task 3: Develop visual order confirmation acknowledgement screen | 10
| Priya | Task 4: Implement data encryption for customer transactions | 15
| Keiko | Task 5: Create order history and status tracking view | 10
0003 Marketing Needs 1 | Lead: Ram | User Story: Real-Time Skin Care Industry Market Trends | 75
| Priya | Task 1: Connect real-time external data feeds for industry trends | 22
| Dev Lead | Task 2: Build visual trend dashboard by skincare product category | 18
| Ram | Task 3: Develop filter for emerging market segments and demographics | 12
| Ram | Task 4: Program feature to estimate long-term product feasibility | 15
| Keiko | Task 5: Enable export function for trend intelligence reports | 8
0004 Marketing Needs 2 | Lead: Ram | User Story: Customer Interest and Preference Opinion Analysis | 74
| Dev Lead | Task 1: Build customer opinion and review collection function | 20
| Ram | Task 2: Program sentiment analysis for customer preferences | 18
| Ram | Task 3: Develop brand perception tracking dashboard | 14
| Jose | Task 4: Create demographic profiling display for buyers | 12
| Keiko | Task 5: Tag customer feedback for new product concept testing | 10
0005 Marketing Needs 3 | Lead: Priya | User Story: Competitive Analysis and Global Sales Data | 72
| Priya | Task 1: Ingest global sales data feeds into database | 20
| Dev Lead | Task 2: Identify and list competitor products with largest market share | 16
| Ram | Task 3: Develop competitor price and feature comparison screen | 14
| Priya | Task 4: Program automated alerts for competitor market shifts | 12
| Jose | Task 5: Generate competitive benchmark summary report | 10
0006 Marketing Needs 4 | Lead: Cal | User Story: Calculate AHI Market Share and Category Trends | 72
| Dev Lead | Task 1: Program AHI market share calculation formula by product category | 18
| Ram | Task 2: Build dashboard to evaluate sales, financial, and market data | 16
| Ram | Task 3: Develop 4-P decision support display (product, price, place, promotion) | 16
| Cal | Task 4: Compare AHI market share trends against industry growth (4.5%–7.5%) | 12
| Cal | Task 5: Conduct sprint prototype demonstration and sign-off | 10
User Story
Task 1
Task 2
Task 3
Task 4