## WBS
|  | AHI Real-Time Marketing Data Application Project |  |  | Level 1 Project level
1.0 Design Phase (30 days) | 2.0 Development Phase (90 days) |  | 3.0 Test Phase (30 days) | 4.0 Launch and Approve the App Phase (60 days) | Level 2 Phase level
1.1 Define key app functionality requirements | 2.1 Implement IT upgrades |  | 3.1 Begin full-scale development | 4.1 Finalize new hires | Level 3 Work package level
1.2 Identify vendor to design and develop app | 2.2 Develop an initial prototype |  | 3.2 Test the final app prototype | 4.2 Launch a new app
1.3 Finalize vendor contract | 2.3 Perform prototype beta test |  | 3.3 Begin IT hiring | 4.3 Monitor app performance
1.4 Develop initial design | 2.4 Solicit beta test feedback |  | 3.4 Gain customer acceptance | 4.4 Document app issues
1.5 Solicit initial design feedback | 2.5 Update prototype based on feedback |  | 3.5 Approve the launch plan | 4.5 Plan app upgrades
1.6 Update design based on feedback | 2.6 Gain prototype sign-off |  | 3.6 Train Marketing personnel on a new app | 4.6 Implement app upgrades