## Phase 1
Project Management Notes & Legend:
Note 1: Sequence & Logic | Tasks follow strict finish-to-start (FS) or parallel dependency logic derived from the approved WBS.
Note 2: Critical Path (RED) | Red boxes represent the Critical Path with Total Float = 0. Any delay impacts overall project delivery.
Note 3: Non-Critical Path (BLUE) | Blue boxes represent parallel activities with float (slack) that do not delay downstream critical gates.
Note 4: Buffer Days (YELLOW/OVAL) | Buffer ovals absorb feedback triage, integration, and testing risks to protect fixed milestone commitments.
Note 5: WBS Reconciliation | The number of activities shown in this network diagram exactly equals the number of WBS activities.
1.1 Define Requirements (4d)
1.2 Identify Vendor (4d)
Plan next steps
Start
Design
1.3 Finalize Contract (4d)
1.4 Develop Initial Design (6d)
1.5 Solicit Feedback (3d)
3 Days Buffer
1.6 Update Design (4d)
1.6 Update Design (4d)
1.7 Gain Final Approval (2d)

## Phase 2
2.1 Implement IT Upgrades (25d)
Start Development
2.3 Beta Test (15d)
2.2 Develop Prototype (35d)
5 Days Buffer
2.5 Update Prototype (15d)
2.4 Solicit Feedback (5d)
2.6 Sign-off (5d)
2.7 Launch Plan (10d)

## Phase 3
3.1 Full-Scale Dev (8d)
Start Test Phase
3.2 Test Final Prototype (10d)
3.3 Begin IT Hiring (12d)
3 Days Buffer
3.5 Approve Launch Plan (5d)
3.4 Customer Acceptance (4d)
3.6 Train Personnel (8d)

## Phase 4
4.1 Finalize New Hires (10d)
Start Launch
4.3 Monitor Performance (15d)
4.2 Launch New App (5d)
5 Days Buffer
4.5 Plan Upgrades (8d)
4.7 Plan v2 Upgrades (4d)
4.6 Implement Upgrades (10d)
4.4 Document Issues (5d)
4.8 Launch App v2 (4d)
4.9 Complete Final Report (4d)

## Sheet5
AHI REAL-TIME MARKETING DATA APPLICATION - NETWORK DIAGRAM SUMMARY
Phase | WBS Reference | Total Duration | Critical Path Duration | Lifecycle Model | Direct Cost Allocation | Key Milestone Sign-off
1.0 Design Phase | Tasks 1.1 to 1.7 | 30 Days | 30 Days (incl. 3d Buffer) | Predictive / Hybrid | 50% App Development ($90,000) | Final Design Approval
2.0 Development Phase | Tasks 2.1 to 2.7 | 90 Days | 90 Days (incl. 15d Buffers) | Adaptive (Scrum) & Predictive | IT HW/SW ($15,000) & Data Feeds ($5,000) | Prototype Sign-off
3.0 Test Phase | Tasks 3.1 to 3.6 | 30 Days | 30 Days (incl. 3d Buffer) | Predictive / Quality Gate | IT Storage ($15,000) & Security ($20,000) | Customer Acceptance
4.0 Launch & Approve | Tasks 4.1 to 4.9 | 60 Days | 60 Days (incl. 5d Buffer) | Adaptive / Operations | 50% App Dev ($90,000) & IT HR ($15,000) | App v2 Launch & Final Report
TOTAL PROJECT | 29 WBS Tasks + Buffers | 210 Days | 210 Days Total Critical Path | Hybrid Lifecycle | $250,000 Total Approved Budget | Project Closeout Complete